## tabella
Progetto FitDiary | Project Manager: Salvatore Fasano, Gianluca Spinelli
| Consegna Intermedia (RAD, SDD, TP e TCS) | First Status Report (Source code e Testing) | Final Status Report (Consegna Finale)
Metric | 15/12/2021 | 09/01/2022 | 24/01/2022
Budget at Completion (BAC) | 3920 | 13720 | 14000
Earned Value (EV) | 3920 | 9518.936 | 14000
Actual Cost (AC) | 3990 | 9485 | 13860
Planned Value (PV) | 3920 | 9485 | 14000
%Progress | 100% | 69.38% | 100%
Cost Variance (CV) | -70 | 33.936 | 140
Schedule Variance (SV) | 0 | 33.936 | 0
Cost Performance Index (CPI) | 98.25% | 100.4% | 101%
Schedule Performance Index (SPI) | 100% | 100.4% | 100%
Estimate to Completion (ETC) | 0 | 4186.0868 | 0
Estimate at Completion (EAC) | 3990 | 13671.0868 | 13860
Variance at Completion (VAC) | -70 | 48.9132 | 140
Average Index | 0.99123 | 1.0036 | 1.0051
Stato | YELLOW | GREEN | GREEN
Nota | Il ritardo è stato dovuto alla difficoltà da parte dei Team Members nel design della struttura del Database | Durante la fase di ODD è stato recuperato il ritarto dell'SDD e ciò ho portato ad un guadagno maggiore di circa 1 ora sull'EV (35€ circa) | Il progetto si è concluso con quattro ore di anticipo (ottenute durante la fase di stesura di alcuni documenti di testing sovrastimati)